## Sheet1
Tasks | 10:00 | 10:20 | 10:40 | 11:00 | 11:20 | 11:40 | 12:00 | 12:20 | 12:40 | 14:00 | 14:20 | 14:40 | 15:00 | 15:20 | 15:40 | 16:00 | 16:20 | 16:40 | 17:00
LCD Hello world
LCD help
Measurements for front pannel and buttons ect
Laser cutting solder stencil
Testing assembly and reflow
Stencil help
Connect Radio
Code missing functions
Test radio functions
Implement keypad
Deliverables: | For lab session: | [5 empty] | Outside lab session:
Seb: | Working Radio interface | [5 empty] | CAD Design for front pannel | [8 empty] | Phil Handley
| Working keypad | [5 empty] | PCB Review | [8 empty] | Sebastian Goscik
Stuart: | Working LCD Display | [5 empty] | PCB Design & review | [8 empty] | Stuart Reyner
Phil: | All measurements for CAD design | [5 empty] | CAD Design for front pannel | [7 empty] | X | Not present
| Working solder stencil process | [5 empty] | PCB Design