## Sheet1
Task | Start | Duration | End
MPLab | 0 | 6 | 6
Inputs | 6 | 1 | 7
PIC Setup | 7 | 5 | 12
I2C Implementation | 12 | 6 | 18
LCD Implementation | 18 | 6 | 24
Debugging & Testing | 24 | 6 | 30
Amplifier | 0 | 6 | 6
LCD | 6 | 12 | 18
Front Panel | 18 | 6 | 24
Debugging & Testing | 24 | 6 | 30
I2C Setup | 0 | 6 | 6
Radio I2C | 6 | 6 | 12
RDS | 12 | 6 | 18
Keypad | 18 | 6 | 24
Recorder | 24 | 6 | 30
PCB Design | 6 | 3 | 9
PCB Review & Order | 9 | 1 | 10
PCB Slack (Design & Review) | 10 | 8 | 18
PCB Fabrication | 18 | 12 | 30
PCB Stencil | 10 | 3 | 13
PCB Slack (Stencil) | 13 | 17 | 30
Component Ordering | 10 | 1 | 11
Component Slack | 11 | 19 | 30
PCB Assembly | 30 | 6 | 36
Final Construction | 36 | 6 | 42

## Sheet2
Tasks completed |  | Tasks removed | Tasks slipped
MPLab |  | RDS | PCB Design
PIC setup |  |  | PCB Review
I2C Implementation |  |  | LCD
Amplifier
I2C Setup
Radio I2C
Component Ordering
Last updated | 2015-03-02