## Sheet1
Tasks | 10:00 | 10:20 | 10:40 | 11:00 | 11:20 | 11:40 | 12:00 | 12:20 | 12:40 | 14:00 | 14:20 | 14:40 | 15:00 | 15:20 | 15:40 | 16:00 | 16:20 | 16:40 | 17:00
LCD Hello world
LCD help
Laser cutting front panel
Laser cutting solder stencil
Testing assembly and reflow
Stencil help
Connect Radio
I2C Test
Test radio functions
Implement keypad
Deliverables: | For lab session: | [5 empty] | Outside lab session:
Seb: | Working Radio interface | [14 empty] | Phil Handley
| Working keypad | [14 empty] | Sebastian Goscik
Stuart: | Working LCD Display | [14 empty] | Stuart Reyner
Phil: | Cut front panel | [13 empty] | X | Not present
Succesfully reflowed test PCB.